## GANTT
Weeks, monday to monday
| Starting week | Ending week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  |  | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24
Deliveries date | 1 | 20
Rubric 1 | 1 | 5
Rubric 2 | 6 | 12
Rubric 3 | 13 | 17
Bachelor's thesis delivery | 18 | 20
Memory | 1 | 19
Introduction | 3 | 3
State of art | 1 | 2
Project management | 1 | 2
Methodology | 3 | 4
Project development | 5 | 17
Conculsions | 18 | 19
Research | 1 | 5
Bachelor's thesis lessons | 1 | 4
Competence research | 1 | 3
Art assets research | 3 | 5
Particle effects research | 8 | 8
Design | 5 | 19
Player | 5 | 5
Enemies | 5 | 5
Maps | 5 | 5
UI (User Interface) | 5 | 5
Items | 5 | 5
1st map tileset | 5 | 5
1st map inside Unity | 6 | 6
2nd map tileset | 6 | 6
2nd map inside Unity | 16 | 16
3rd map tileset | 6 | 6
3rd map inside Unity | 16 | 16
Environment sounds/FX's | 5 | 5
Missing map sprites | 6 | 6
Particle effects creation | 8 | 8
Balancing | 18 | 19
Programming | 6 | 20
Players animations | 6 | 6
Enemies animations | 7 | 7
Player base movement | 6 | 6
Put enemies in game | 7 | 7
Enemies AI | 9 | 11
Player skills | 6 | 8
Enemies skills | 10 | 11
Level up system | 8 | 8
Items system | 12 | 12
Release playtesting | 13 | 13
Release Delivery 3 | 17 | 17
Polish | 18 | 19
Final Release | 20 | 20
Main menu UI | 13 | 13
Player level up UI | 8 | 8
Skills UI | 8 | 8
Items UI | 13 | 13
Environment sounds | 13 | 13
Player FX's | 13 | 13
Enemies FX's | 13 | 13
UI FX's | 14 | 14
World FX's | 13 | 13
Enemies HP bar's | 7 | 7
Player respawn system | 9 | 9
Checkpoints | 9 | 9
Scene management | 9 | 10
Map interactions | 2019-07-14 | 2019-08-15
Testing | 12 | 15
Enemies AI | 12 | 12
Combat | 12 | 13
Google form for playtesting | 13 | 13
Select playtesting users | 13 | 13
Personal playtesting | 12 | 13
External playtesting | 14 | 14
Analyze external playtesting | 15 | 15
Bugs | 7 | 17
Combat | 12 | 14
Post-Testing bugs | 15 | 17
Other probable bugs | 2019-07-15 | 2019-11-17